## Risks
trAIner Risk List
Risk ID	Date Identified	Headline	Description	Type	Impact	Probability	Magnitude	Owner	Mitigation Strategy
1	2018-10-11	Wrong development platform	It is possible that the chosen development platform might be short of some libraries that could make the development process a lot easier.	Resource	1	20%	0.2		Doing some research beforehand to make sure the most suitable development platform was chosen
2	2018-10-11	AI computing speed	The artificial intelligence logic might have to process a lot, which in turn could slow down the user interface & therefore affect the user experience	Technical	4	60%	2.4		Making sure that some processes & computations will be handled in background threads
3	2018-10-11	Fun factor	It is possible that the game becomes boring after playing a certain amount of time	Business	5	80%	4.0		Develop a lot of different levels/maps & making sure the leaderboards won’t stay the same over a long period of time
4	2018-10-11	Team size & knowledge	A small team might not accomplish as much as a bigger team, however, the bigger the team the more misunderstandings might occur. / Also the knowledge of the team members on certain algorithms, AI, structured coding might cause problems	Technical	3	30%	0.9		Team members should understand at least 80% of the code & if problems occur team members should always help each other out.
5	2018-10-11	Schedule	To develop certain depths & testing of a game there is no question that a lot of time is required & all the team members also have other projects to work on.	Schedule	3	40%	1.2		Each team member should have a flexible schedule so that each week they can make progress with the project.
6	2018-10-11	Inadequate specification	It is possible that some team members have different ideas on how the game should work & look due to inadequate specification	Business	3	30%	0.9		Specify a very complete description of the game with the help of use cases & team member discussions of the vision
7					0.0
8					0.0
9					0.0
10					0.0
11					0.0
12					0.0
13					0.0
14					0.0
15					0.0
16					0.0
17					0.0
18					0.0