## Product Backlog
ID	Description	Priority	Effort (hours)		Status	Remark
			estimated	required
1	As a player I want to create an empty map where I could later put building blocks in order to complete my custom map	5	20		done	Designing of the map area is coding stage.
2	As a player I want to have a side navigation bar so that I could select different building blocks that could be easily dragged and dropped on to the map	5	25	24	done	The navigation GUI part implemented. Sidebar done.
3	As a player I want to easily place the building blocks on to the map by dragging and dropping them	5	15		done	The map also will contain the starting point
4	As a player I want to save my created map so I could train my AI on it	5	17	22	done
5	As a player I want to load any of my saved maps	5	2	5	done	Saved maps in CSV format.
6	As a player I want to be able to edit my already created maps	3	10	10	done
7	As a player I want to start training the AI on a preloaded map whenever I press play	5	30	37	done
8	As a player I can adjust the learning parameters of the AI	4	15	40	done
9	As a player I want the AI to 'mutate' automatically if it doesn't reach the goal	5	22	45	done
10	As a player I want my AI to be able to compete on a pre-built challenge map in order to get upgrades	5	25		in progress	basically done, only UI part needs to be implemented
11	As a player I want to be rated whenever I finish a pre-built challenge map and be put on a scoreboard	2	10		to do	dropped, due to lack of time
12	As a player I want to receive power ups after successfully completing challenges	2	10		to do	dropped, due to lack of time
13	As a player I can play with all suitable peripherals	4	8	8	done

## Sprint 1
Sprint 1

Starts
Ends
Overall Goal	Create a map builder interface

User Stories that are part of this sprint:
ID	Description	Acceptance Criteria				Status
1	As a player I want to create an empty map where I could later put building blocks in order to complete my custom map.	The user can customize an empty map.				done
2	As a player I want to have a side navigation bar so that I could select different building blocks	User can see different items in the side bar				in progress
3	As a player I want to easily place the building blocks on to the map by dragging and dropping them	It is possible to build map with different types of Map elements				in progress
4	As a player I want to start training the AI on a preloaded map whenever I press play					in progress

Sprint Backlog (Tasks)
ID	Description	User Story ID	Effort (hours)		Status	Persons
			estimated	required
1	create a map containing a grid to hold objects	1	5	10	finished
2	propose an app design solution	1	6	8	finished
3	define behavior for the obstacles	1	5	7	in progress
4	Add building blocks and other obstacle objects	2	5	5	in progress
5	Add drag and drop functionalities	3	5		in progress
6	create a pane for the side navigation	2	5	5	finished
7	add draggable elements to the navigation bar	2	5		in progress
8	define basic genetic algorithm behavior	4	20	25	in progress

## Sprint 2
Sprint 2

Starts	2018-11-01
Ends	2018-11-15
Overall Goal	Finish map building interface, finalize basic AI functionality

User Stories that are part of this sprint:
ID	Description	Acceptance Criteria				Status
1	As a player I want to create an empty map where I could later put building blocks in order to complete my custom map.	The user can customize an empty map.				in progress
2	As a player I want to have side navigation bars so that I could select different building blocks	User can see different items in the side bar				in progress
3	As a player I want to easily place the building blocks on to the map by dragging and dropping them	It is possible to build map with different types of Map elements				in progress
4	As a player I want to start training the AI on a preloaded map whenever I press play					done

Sprint Backlog (Tasks)
ID	Description	User Story ID	Effort (hours)		Status	Person(s)
			estimated	required
1	Add Junit tests to the java project		20	20	done	Patrick, Lucas
2	implement right bar functionality (select game mode, adjust parameters)	2	7	8	done	Patrick,Rahul, Kaspar
3	Implement design of the topbar	2	5	5	done	Kasparas
4	implement design of bottom bar	2	5	5	done	Rahul
5	finish dragging and dropping of building blocks	3	10	12	done	Kasparas
6	initialize an empty map	1	2		done
7	finalize saving and loading of the maps	1	5	22	done	Sascha
8	add behavior of different map elements	3	10	3	done	Kasparas
9	make the GA move the individuals to the finish	4	15	35	done	Lucas
10

## Sprint 3
Sprint 3

Starts	2018-12-13
Ends	2019-01-03
Overall Goal	make the game playable

User Stories that are part of this sprint:
ID	Description	Acceptance Criteria				Status
1	As a player I want to create an empty map where I could later put building blocks in order to complete my custom map	empty map gets created				done
2	As a player I want the AI to 'mutate' automatically if it doesn't reach the goal	GA moves to the goal by itself and reproduces				done
3	As a player I want to easily place the building blocks on to the map by dragging and dropping them	creating a map in game works				done
4	As a player I want my AI to be able to compete on a pre-built challenge map in order to get upgrades	switch game mode to play on the challenge maps				in progress

Sprint Backlog (Tasks)
ID	Description	User Story ID	Effort (hours)		Status	Person(s)
			estimated	required
1	further enhancement of the Junit tests	-	27	22	in progress	Patrick
2	implement dragging and dropping of the building blocks	3	20	15	done	Kasparas, Patrick
3	improve AI behavior when mutating	2	20	25	done	Lucas, Kasparas
4	create pre-built challenge maps	4	10	10	done	Sascha, Rahul
5	create a game mode for challenges	4	10	-	to do	Sascha, Rahul
6	initialize an empty map	1	5	6	done	Sascha
7	implement placement of building blocks	3	10	11	done	Kasparas, Patrick
8	set up reproduction of the AI after the generation finishes	2	12	16	done	Lucas

## Sprint 4
Sprint 2

Starts	2018-11-01
Ends	2018-11-15
Overall Goal	Finish map building interface, finalize basic AI functionality

User Stories that are part of this sprint:
ID	Description	Acceptance Criteria				Status
1	As a player I want my AI to be able to compete on a pre-built challenge map in order to get upgrades	visually switch between game modes				done
2	As a player I can adjust the learning parameters of the AI	parameters can be adjusted while the game is live				done

Sprint Backlog (Tasks)
ID	Description	User Story ID	Effort (hours)		Status	Person(s)
			estimated	required
1	create a game mode for challenges	1	10	-	done	Sascha, Rahul
2	visually show switching and current game mode	1	10	10	done	Patrick, Kasparas, Lucas
3	improve performance of the genetic algorithm, i.e. make it move faster to the finish	-	15-35	25	done	Lucas, Kasparas
4	further enhancement of the Junit tests	-	36		in progress	Patrick
5	debugging		35	35	done	Lucas, Patrick, Kasparas
6	enhancements of the UI and the UX i.e. icons, buttons, pop ups etc. …		17	20	done	Kasparas
7	conceptualize a demo of the application		4	4	done	Lucas, Patrick, Kasparas
8	make a poster		5	3	done	Kasparas
9	improve documentation, refactoring		12	4	done	everybody

## Sprint copy template
Sprint 1

Starts	2018-11-01
Ends	2018-11-15
Overall Goal	Improve user profile functionality

User Stories that are part of this sprint:
ID	Description	Acceptance Criteria				Status
1	As a registered user I want to set-up a personal profile page to present myself.	User can define and view profile page with profile picture and self description.				in process
					done
					to do
					accepted

Sprint Backlog (Tasks)
ID	Description	User Story ID	Effort (hours)		Status	Person(s)
			estimated	required
1	Extend database with fields for profile info	1	3	5	done	Philipp Graf
2	Develop form to fill in profile data in HTML	1	6		in process	Anja Müller
3	Add form and logic for save / edit to application	1	3		to do