## Product Backlog
ID	Description	Priority	Effort (hours)		Status	Remark
			estimated	required
1	As a player I want to create an empty map where I could later put building blocks in order to complete my custom map	5	10		in process	Designing of the map area is coding stage.
2	As a player I want to have a side navigation bar so that I could select different building blocks that could be easily dragged and dropped on to the map	5	5		in process	The navigation GUI part implemented.
3	As a player I want to easily place the building blocks on to the map by dragging and dropping them	5	10		in process	The map also will contain the starting point
4	As a player I want to save my created map so I could train my AI on it	5	5		to do
5	As a player I want to load any of my saved maps	5	2		in process	Saved maps in CSV format.
6	As a player I want to be able to edit my already created maps	3	2		to do
7	As a player I want to start training the AI on a preloaded map whenever I press play	5	30		to do
8	As a player I can adjust the learning parameters of the AI	4	15		to do
9	As a player I want the AI to 'mutate' automatically if it doesn't reach the goal	5	20		to do
10	As a player I want my AI to be able to compete on a pre-built challenge map in order to get upgrades	5	25		to do
11	As a player I want to be rated whenever I finish a pre-built challenge map and be put on a scoreboard	3	10		to do
12	As a player I want to receive power ups after successfully completing challenges	2	5		to do
13	As a player I can play with all suitable peripherals	4	3		to do

## Sprint 1
Sprint 1

Starts	2018-11-01
Ends	2018-11-15
Overall Goal	Improve user profile functionality

User Stories that are part of this sprint:
ID	Description	Acceptance Criteria				Status
1	As a registered user I want to set-up a personal profile page to present myself.	User can define and view profile page with profile picture and self description.				in process
					done
					to do
					accepted

Sprint Backlog (Tasks)
ID	Description	User Story ID	Effort (hours)		Status	Person(s)
			estimated	required
1	Extend database with fields for profile info	1	3	5	done	Philipp Graf
2	Develop form to fill in profile data in HTML	1	6		in process	Anja Müller
3	Add form and logic for save / edit to application	1	3		to do

## Sprint x (copy template!)
Sprint 1

Starts
Ends
Overall Goal	Create a map builder interface

User Stories that are part of this sprint:
ID	Description	Acceptance Criteria				Status
1	As a player I want to create an empty map where I could later put building blocks in order to complete my custom map.	The user can customize an empty map.				in process
2	As a player I want to have a side navigation bar so that I could select different building blocks that could be easily dragged and dropped on to the map	User can drag and drop Items from sidebar				in process
3	As a player I want to easily place the building blocks on to the map by dragging and dropping them	It is possible to build map with different types of Map elements				in process

Sprint Backlog (Tasks)
ID	Description	User Story ID	Effort (hours)		Status	Persons
			estimated	required
1	Adding customizable features	1			in process
2	Add building blocks and other obstacle objects	2			in process
3	Add drag and drop functionalities	3			in process